## RSO App Moden. Obser. Developme
SL | FR No | API/ Web/ App | Observation | Status | Remarks
1 | FR 20 | API + App | 1. Retailer demand status remain unchanged in retail app after delivering the product, In RSO app fulfilled demands carts needs to cleared out from the list.
2 | FR 1 | API | 1. API- For EV Return (BalancedReturnRSOList) need Status Code.
3 |  | API | 2. API- In the EV Return API (SaveStockReturn) the response must be in corrected format (Status Code, Message, Data in the Object).
4 |  | API/ Web/ App | 3. Users Matrix (RSO, Merchandiser, Supervisor, ZM) Development for "Notification", "Current Offer", and "Commission Structure".
5 | FR 16 | API | 1. Need Completed API to Provide Site location, Distributor location, retailer location in app
6 | FR 5 | API/ Web/ App | 1. Users Matrix (RSO, Merchandiser, Supervisor, ZM) Development for "Notification", "Current Offer", and "Commission Structure".
7 | FR 7 | API/ Web/ App | 1. Users Matrix (RSO, Merchandiser, Supervisor, ZM) Development for "Notification", "Current Offer", and "Commission Structure".
8 | FR 9 | API/ Web/ App | 1. Users Matrix (RSO, Merchandiser, Supervisor, ZM) Development for "Notification", "Current Offer", and "Commission Structure".
9 | FR 1 | API/ App | 1. Need Change for Stock Update of RSO RSO can not stock Itopup, need to remove itopup validation.
10 |  | API/ App | 2. For DD all RSO Itopup balance list must show.
11 |  | API/ App | 3. DD can see all RSO Itopup balance list then click on a specific RSO, enter DD pin, can edit the balance, and Return the balance after confirmation.
12 | FR 29 | Web | 1. Need change in the web, need multiple Campaign Notice upload and save feature in one UI page.
13 | FR 2 | Web | 1. Web+App- Year uploaded 2000 on web changes to 1990 year.

## New Added JS File Name
JS File Name | Permission Code | Permission Name | New Permission Assign Code
RsoBarUnbarCtrl.js | 4009' | GetPermission('04009') Page load one time call | 04043'
RsoCodeAndDateOfBirthUploadCtlr.js |  |  | 04044'
RetailerPinUnPinBarUnBarCtlr.js | 00701' | GetPermission('04009') Page load one time call | 04045'
ApproveDistributorGPSUpdateCtlr.js | 00201' | GetPermission('00201') Page load one time call | 04046'
BulkDistributorDataUploadCtlr.js |  |  | 04047'
TargetSetupForMerchandiserCtlr.js | 01701' | GetPermission('01701') Page load one time call | 04048'
NoticeBoardNewCtrl.js | 04009' | GetPermission('04009') Page load one time call | 04049'

## Summary
STATUS | Task count | Percent %
#REF! | 0 | 0
#REF! | 0 | 0
#REF! | 0 | 0
#REF! | 0 | 0
#REF! | 0 | 0
#REF! | 0 | 0
#REF! | 0 | 0
#REF! | 0 | 0
#REF! | 0 | 0
Total | 0 | 0
Count of STATUS | STATUS
Task Scope | DEVELOPMENT DONE | NOT START | READY FOR UAT | UAT FEEDBACK INC | WORKING | Grand Total
APK |  | 28 | 1 | 1 |  | 30
Data Process |  | 5 |  |  | 6 | 11
Database |  | 3 |  |  | 1 | 4
Web | 2 | 5 |  | 2 | 1 | 10
Web API |  | 18 |  | 2 | 12 | 32
Web API only |  | 1 |  |  |  | 1
Grand Total | 2 | 60 | 1 | 5 | 20 | 88
Count of STATUS | STATUS
FR1 | DEVELOPMENT DONE | NOT START | READY FOR UAT | UAT FEEDBACK INC | WORKING | Grand Total
FR 1 |  | 16 |  |  | 18 | 34
FR 11 |  |  |  |  | 1 | 1
FR 12 |  |  | 1 | 5 | 1 | 7
FR 13 |  | 5 |  |  |  | 5
FR 15 |  | 1 |  |  |  | 1
FR 19 |  | 4 |  |  |  | 4
FR 22 |  | 2 |  |  |  | 2
FR 23 |  | 7 |  |  |  | 7
FR 24 |  | 3 |  |  |  | 3
FR 25 |  | 3 |  |  |  | 3
FR 26 |  | 16 |  |  |  | 16
FR 8 | 2 | 2 |  |  |  | 4
(blank) |  | 1 |  |  |  | 1
Grand Total | 2 | 60 | 1 | 5 | 20 | 88
FR1 | Count of STATUS
FR 1 | 34 | #REF!
FR 11 | 1
FR 12 | 7
FR 13 | 5
FR 15 | 1
FR 19 | 4
FR 22 | 2
FR 23 | 7
FR 24 | 3
FR 25 | 3
FR 26 | 11
FR 8 | 4
(blank) | 1
Grand Total | 83
Application Status(30-NOV-22)
| Sl | Application checklist | Checked Status | Have Issue(Yes/No) | Remarks
| 1 | POS-DMS SIM Sync process | Checked | No
| 2 | POS-DMS SC Sync process | Checked | No
| 3 | Deno wise pending SMS ongoing status | Checked | No
| 4 | VOMS SC activation checking and Re try process and log file delete | Checked | Yes
| 5 | DBSSAPI physical product deduction process check | Checked | No
| 6 | All Servers status check and log file delete. | Checked | No
| 7 | Daily SC activation data availability check | Checked | No
| 8 | Daily EV data availability check | Checked | No
| 9 | Daily RSO App ETL data availability check | Checked | No
| 10 | POS and DMS JOB broken status check | Checked | No
| 11 | POS and DMS Table Space check | Checked | No
| 12 | RSO App EV Service status check | Checked | No
| 13 | Daily RSO Visit plan data availability | Checked | No
| 14 | Sales dashboard D-1 data availability | Checked | No
Application Status(30-NOV-22)
Sl | Application checklist | Checked Status | Have Issue(Yes/No) | Remarks
1 | POS-DMS SIM Sync process | Checked | No
2 | POS-DMS SC Sync process | Checked | No
3 | Deno wise pending SMS ongoing status | Checked | No
4 | VOMS SC activation checking and Re try process and log file delete | Checked | Yes
5 | DBSSAPI physical product deduction process check | Checked | No
6 | All Servers status check and log file delete. | Checked | No
7 | Daily SC activation data availability check | Checked | No
8 | Daily EV data availability check | Checked | No
9 | Daily RSO App ETL data availability check | Checked | No
10 | POS and DMS JOB broken status check | Checked | No
11 | POS and DMS Table Space check | Checked | No
12 | RSO App EV Service status check | Checked | No
13 | Daily RSO Visit plan data availability | Checked | No
14 | Sales dashboard D-1 data availability | Checked | No
Application Status(30-NOV-22)
Sl | Application checklist | Checked Status | Have Issue(Yes/No) | Remarks
1 | POS-DMS SIM Sync process | Checked | No
2 | POS-DMS SC Sync process | Checked | No
3 | Deno wise pending SMS ongoing status | Checked | No
4 | VOMS SC activation checking and Re try process and log file delete | Checked | Yes
5 | DBSSAPI physical product deduction process check | Checked | No
6 | All Servers status check and log file delete. | Checked | No
7 | Daily SC activation data availability check | Checked | No
8 | Daily EV data availability check | Checked | No
9 | Daily RSO App ETL data availability check | Checked | No
10 | POS and DMS JOB broken status check | Checked | No
11 | POS and DMS Table Space check | Checked | No
12 | RSO App EV Service status check | Checked | No
13 | Daily RSO Visit plan data availability | Checked | No
14 | Sales dashboard D-1 data availability | Checked | No
Database Table Space (1-DEC-2022)
TABLESPACE_NAME | TOTAL_SIZE | FREE_SIZE | PERCENT | YESTERDAY_PERCENT | DAILY_CONSUME_SPACE_GB
KMTDB_DATA | 100 | 13.24 | 13.24 | 13.5 | 0.26
AUDIT_DATA | 15 | 2.61 | 17.4 | 17.4 | 0
VASSMS | 18 | 3.38 | 18.78 | 18.78 | 0
SYSTEM | 2 | 0.46 | 23 | 23 | 0
CFDB_REPORT_DATA_01 | 682 | 176.62 | 25.9 | 26.08 | 1.24
CFDB_IDX | 195 | 61.69 | 31.64 | 31.67 | 0.06
DMSPHASE4_INDEX | 408 | 135.65 | 33.25 | 33.35 | 0.41
APP_DATA_02 | 414 | 140.41 | 33.92 | 34.17 | 1.06
DMSPHASE4 | 698 | 241.99 | 34.67 | 34.72 | 0.35
SMSGATEWAY | 41 | 21.93 | 53.49 | 53.63 | 0.06
SYSAUX | 20 | 11.23 | 56.15 | 56.25 | 0.02
CFDB_DATA | 264 | 149.71 | 56.71 | 56.75 | 0.11
USERS | 10 | 8.64 | 86.4 | 86.4 | 0
UNDOTBS1 | 103 | 99.72 | 96.82 | 97.62 | 0.83
UNDOTBS2 | 33 | 31.98 | 96.91 | 89.94 | -2.3
AMSDB | 15 | 14.74 | 98.27 | 98.27 | 0
NONORACLE | 20 | 19.82 | 99.1 | 99.1 | 0
CDC_DATA | 0.01 | 0.01 | 100 | 100 | 0
AUDIT_ORG | 15 | 15 | 100 | 100 | 0
Application Server Status
Date | Server Name | Check status | C Drive Space | C Drive Free Space | Site / Pool Status | Log Delete | Space After Log Delete | Remarks
2022-12-01 | 172.16.254.167 | Yes | 99.5 GB | Free 58.7 GB | Yes | Yes
| 172.16.254.168 | Yes | 79.5 GB | Free 43.7 GB | Yes | Yes
| 172.16.254.39 | Yes | 119 GB | Free 85.9 GB | Yes | Yes
| 172.16.254.40 | Yes | 99.5 GB | Free 80.6 GB | Yes | Yes
Free GB
| 172.16.7.100 | Yes | 79.5 GB | Free 15 GB | Yes | Yes |  | C drive free space 15 GB
| 172.16.7.123 | Yes | 79.5 GB | Free 34.4 GB | Yes | Yes |  | E drive free space 9.9 GB
| 172.16.7.31 | Yes | 79.5 GB | Free 31.6 GB | Yes | No
| 172.16.11.211 | Yes | 79.3 GB | Free 31.6 GB | Yes | No
| 172.16.8.91 | Yes | 79.5 GB | Free 44.4 GB | Yes | No

## Missing APP DATA
Feature | Remarks | User type
Dashboard | Target vs achievement - Achieved value missing | RSO | Done
Dashboard | Target vs achievement - Achieved data is null | DD | Done
Dashboard | target vs sold - prepaid, sc. Visit plan/visited/memo | RSO | Done
Modality | Campaigns > Comission structure | RSO
Aid Tool | Return memo | RSO | Done
Aid Tool | Sim Status Check | RSO | Done
Monitoring | Target vs achievement - Target data missing | RSO | Done
Monitoring | Bottoms sellers not found | RSO
Operational Report | missing data for all 3 types | RSO | Done
Earning | Rso comission- incentive 0 in all | RSO
Earning | RSO Earning - multiple times months, and multiple data for a month | RSO |  | Need API name
Retailer Demand | No data or api update needed to get all retailer demands to RSO | RSO | Done
Retailer panel | Report > Comission, itopup history, sales memo > no data | RSO
Retailer panel | Offers | RSO
Retailer panel | Retailer best practices data missing | RSO
Top Sellers | "GET_KPI_STATUS" api error | DD | Done
EV Return | data missing | DD | Done
Dashboard | dashboard no data, error | DD | Done
Route | no routes /retailer | Merchendizer
Dashboard | dashboard no data, error | Merchendizer

## Issue
SN | Menu | Issues | Status | Remark
1 | Dashboard | Today's Highlight ---Same heading | Done
2 | Dashboard | Distributor Notification Issue
3 | Dashboard | Notification does not show selecting for a single DD (SS International) -- (Comes for all)
4 | Modelity | Update Current offer [Multiple data shows if one uploaded]
5 | Monitoring | Route Performance (No data found)
6 | Monitoring | Target VS Achivement (App design Issue) | Pending
7 | Monitoring | Top-Bottom Seller should be removed from Monitoring menu(For DD user)
8 | Report (App) | Top-Bottom Seller (For distributor login) --Data not found
9 |  | Retailer Transcation Bearring | Pending | API 500 error
Below FRS as per BRS
10 | FR-2 | Web Report
11 | FR-3 | Last Month (App side) | Done
12 | FR-4 | Lat-Long (Issue)
13 | FR-5 | point .6 --> App | Pending | api error
14 | FR-5 | Point .7 --> Web
15 | FR-10 | App side | Pending | updated
16 | FR-11 | App side (d-1 and Long Balance ) | Done
17 | FR-12 | App Side Checking | Pending | dd pin
18 | FR-13 | App Side Checking | Pending | dd pin
19 | FR-14 | Live C2C will be used to identify critical retailers (App & Web) | Pending
20 | FR-15 | Need to test
21 | FR-16 | Not done
22 | FR-17 | Need to test
23 | FR-21 | App side | Done
24 | FR-23 | App side (Point-2) | Done
25 | FR-25 | App side | Done
26 | FR-26 | Need to test
27 | FR-29 | RSO earning (App + web) Head wise | Pending | mairaj bhai
28 | FR-30 | Need to test
Below FRS as per SRS
29 | FR-29 | APP Side | Pending | api endpoint
30 | FR-30 | APP Side | Ongoing

## UI Revamp Progress
FR# | QA Status | QA Remarks | Name | Status |  | API Status | API Remarks | Functional Status | Func Remarks
| Pending | Need to know the Ad HOC Report data creation in Web Part | Ad HOC Report | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=264%3A1576 | Done |  | Done
| Pending | Need to know some logic | Campaign | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=36%3A242 | Done |  | Done
| Pending | Data Created for Distributor but Showing for DIs. and RSO | Comission Structure | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A953 | Done | GetNotification | Pending | need to update menu name
| Pass | Found Ok for Distributor and RSO | Create password | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=273%3A5493 | Done |  | Done
| Pass | Found Ok for RSO Users | Critical Retailer | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=14%3A462 | Done |  | Done
| Failed | Showing Multiple Same Data for Distributor | Current Offers | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A918 | Done |  | Done
|  |  | Device Register | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=273%3A5455 | Pending | policy url | Done
|  |  | FAQ | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A1708 | Pending |  | Done
| Pass | Found Ok for Distributor and RSO | Login | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=273%3A5475 | Done |  | Done
|  |  | Market Update | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=221%3A2056 | Done |  | Done
| Pending | Currently have no test data. | Memo | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=33%3A218 | Done |  | Done
|  |  | Merchendizer Dashboard | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=411%3A5929 | Pending | (GetTop5IssueProduct) -- Done ,empty data GetRSOTargetVsAchivement, | Done
| Pass | Found Ok for Distributor and RSO | More | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=11%3A36 | Done |  | Done
| Pending | RS0149 B. Date Upadated, Need to check tomorrow | New - Birthday popup |  | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=376%3A4306 | Done |  | Done
FR10 |  |  | New - Complaints | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=375%3A3265 | Done |  | Done
|  |  | New - DD Acknowledgement | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=395%3A4373 | Done |  | Done
|  |  | New - DD Acknowledgement Details | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=395%3A4216 | Done |  | Done
| Pass | Active RSO for DD Found OK, Need to Check RS002861 RSO tomorrow | New - DD Active RSO | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=286%3A4427 | Done |  | Done
| Failed | Either the Page Heading Name should be only CRITICAL or The page data should be only Retailers data | New - DD CRITICAL | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=286%3A4210 | Done |  | Done
|  |  | New - DD Ev Return Request | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=320%3A3214 | Pending |  | Done
|  |  | New - DD Ev Return Request Approve | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=321%3A3809 | Pending |  | Done
| Pending | EV Pin Reset Request should be for RSO. | New - DD PIN Reset | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=321%3A3857 | Done |  | Done
|  |  | New - DD Pin Reset Pin | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=321%3A3985 | Pending | response message is null(ProcessPINresetRequest) EV API Calling problem | Done
| Pass | Found Ok for Distributor User | New - DD Report | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=287%3A4872 | Done |  | Done
| Pass |  | New - DD Report- Inventory | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=287%3A6050 | Done |  | Done
| Pass | Need to know about Tertiary | New - DD Report- Product | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=287%3A5550 | Done |  | Done
| Pass | Page Heading Should be more appropriate like RSO KPI Report, Page Column Headers must not be broken. | New - DD Report- RSO KPI | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=290%3A3261 | Done |  | Done
| Failed | UI and Information are wrong | New - DD Report- Resource | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=287%3A6295 | Done |  | Done
| Pass | District + Thana Sequence is not right | New - DD Report- Site | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=290%3A4727 | Done |  | Done
|  |  | New - DD Suspend | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=352%3A3349 | Pending | api error 500 (SaveRetailerBarringRequest) EV API Calling problem | Pending
|  |  | New - DD Suspend Retailers | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=352%3A3221 | Done |  | Done
FR1 | Pass |  | New - DD Visit Plan | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=286%3A3119 | Done |  | Done
FR1 | Pass |  | New - DD Visited | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=286%3A3379 | Done |  | Done
|  | Only For Merchandiser Users | New - Dismantling | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=411%3A5320 | Done |  | Done
|  |  | New - Map | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=395%3A3272 | Done |  | Done
|  |  | New - Merchdendizer popup | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=411%3A6734 | Done
|  |  | New - Merchendizer Dismantling | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=411%3A5660 | Pending | error 400(SavePosmReturnDismantle ) -- Done | Pending
|  |  | New - Merchendizer POSM | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=408%3A4696 | Done | error 400() | Done
|  |  | New - Merchendizer Return | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=411%3A6201 | Pending |  | Done
|  |  | New - RSO Acknowledgement | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=39%3A251 | Done |  | Done
| Pass | Need to know, In the RSO list all RSO present or Only Active RSO present. | New - DD RSO list | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=375%3A3944 | Done |  | Done
|  |  | New - Rso Site (bottom low 10 performing site) | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=321%3A4472 | Pending | some field not found(TopBottomRetailers-FR 28) -- Done but which field | Pending | api implementation
|  |  | New - View as RSO | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=375%3A4121 | Done |  | Done
|  |  | New - iTopup - Retailer Amount | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=321%3A4278 | Pending |  | Done
|  |  | New - iTopup - Retailer Confirm | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=321%3A4431 | Pending | api error(SaveTopupIssueToRetailer) | Pending
| Failed | Scan Feature is not working | New - iTopup - Retailers | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=321%3A4086 | Done |  | Done
|  |  | New Outlet registration | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=221%3A1813 | Done |  | Pending
|  |  | Notices | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=465%3A3642 | Done |  | Pending | api implementation
| Failed | Message, Flash, and Ticker Notification do not work for Distributor, Message (Found Ok), Ticker (Link does not show), and Flash (Does not work) Notification for RSO. | Notifications | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=13%3A64 | Done |  | Done
|  |  | Notifications - Traffic | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=395%3A3765 | Done
|  |  | Notifications - Weather | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=395%3A3610
|  |  | OTP | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=272%3A3177 | Done |  | Ongoing | resend api implementation
| Pass | Found Ok for RSO | Operational Report | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=264%3A1898 | Done |  | Done
| Pass | Found Ok for RSO | Operational Report - Details | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=52%3A1660 | Done |  | Done
| Pending | Need to know logic for RSO Best Practices data(RSO or Retailer) | RSO Best Practices | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=135%3A705 | Done |  | Done
|  |  | RSO Comission Summary | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=83%3A1255 | Done |  | Done
|  |  | RSO Dashboard | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=275%3A3089 | Done |  | Done
| Pass |  | Retailer - Checkout | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=217%3A1393 | Done |  | Done
| Pass |  | Retailer - Complaint | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=61%3A1732 | Done |  | Done
|  |  | Retailer - Dashboard | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=201%3A797 | Done |  | Done
|  |  | Retailer - Device Return | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=222%3A2266 | Done |  | Done
|  |  | Retailer - ITopup Delivery | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1009 | Done |  | Done
|  |  | Retailer - Info | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=220%3A1643 | Done |  | Done
|  |  | Retailer - Location Update | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=98%3A578 | Done |  | Done
|  |  | Retailer - Offer | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=61%3A1487 | Done |  | Done
|  |  | Retailer - Products | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1145 | Done |  | Done
|  |  | Retailer - Report | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=61%3A1377 | Done |  | Done
|  |  | Retailer - Report Comission | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1060 | Done |  | Done
|  |  | Retailer - Report Lifting | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1077 | Done |  | Done
|  |  | Retailer - Report Memo | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1128 | Done |  | Pending
|  |  | Retailer - Report SAF | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1094 | Done |  | Done
|  |  | Retailer - Report Stock | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1043 | Done |  | Done
|  |  | Retailer - Report itopup | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1111 | Done |  | Pending | data not show in ui
|  |  | Retailer - SC Delivery | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=203%3A1026 | Done |  | Pending | date format exception
|  |  | Retailer - Sim Delivery | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=222%3A2007 | Pending | error 500(GetProductFromSl) | Done
|  |  | Retailer - Sim Return | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=222%3A1911 | Done | Not check | Pending
|  |  | Retailer Best Practices | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=135%3A841 | Done |  | Done
|  |  | Retailer's Demand | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A820 | Done |  | Done
|  |  | Return Memo | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A988 | Done | empty list (GetReturnMemo ) | Pending
|  |  | Route performace | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=53%3A1305 | Done |  | Done
|  |  | Routes | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=35%3A537 | Done |  | Done
|  |  | Routes Filter | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=35%3A1420 | Done |  | Done | bug on route filter
|  |  | SR-Balance | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=178%3A853 | Done |  | Done
|  |  | Sim Status Check | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=222%3A1287 | Done |  | Done
|  |  | Splash | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=272%3A972 | Done |  | Done
|  |  | Stock | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=54%3A618 | Done |  | Done
|  |  | Stock - Add Stock | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=222%3A977 | Done |  | Done
|  |  | Stock - Return Stock | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=107%3A817 | Done |  | Done
|  |  | Survey | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A1026 | Done |  | Done
|  |  | Target Vs Achievement | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=53%3A868 | Done |  | Done
|  |  | Top Bottom | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A1408 | Pending | empty bottom seller data (TopBottomRetailers when TOP_BOTTOM_OPTION != ) | Pending
|  |  | Training | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=53%3A1466 | Pending |  | Done
|  |  | Transaction - Today’s Sales Report | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A1556 | Done
|  |  | Transaction - Topup History | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=163%3A1545 | Done
|  |  | Visit Plan | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=15%3A1250 | Done |  | Done
|  |  | Visited Plan | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=367%3A3550 | Done |  | Done
12 |  |  |  | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=321%3A3857
|  |  | EV Pin Unbar Request | Done | https://www.figma.com/file/E2PrL2IPzu2WFEYowF8SVb/RSO-APP?node-id=320%3A3589 | Done |  | Done
|  |  | DD Stock - Add Stock |  |  | Done |  | Done

## Task List
SL | FR1 | FR | Task Scope | Title | SUB Category | TIME LINE | RESPONSE BY | STATUS | STATUS2 | Remarks | Support Team
1 | FR 1 | 1 | Database | Login credentials as per dms (DD) | Login credentials as per dms (DD Master SIM, DD code) |  |  | NOT START
2 | FR 1 | 1 | Database | • Device Registration, Forget Password, Password reset option • MasterSIM field in DMS for SMS / PIN/ Password | • Device Registration, Forget Password, Password reset option • MasterSIM field in DMS for SMS / PIN/ Password |  |  | NOT START
3 | FR 1 | 1 | Database | • Same New UI will be applied for this App also | Same UI as like RSO Sum of all RSO of DD (visit, Target vs sold, Critical Retailer, target vs Achievement) |  | Arif | NOT START
4 | FR 1 | 1 | Web API | • Same New UI will be applied for this App also | Same UI as like RSO Sum of all RSO of DD (visit, Target vs sold, Critical Retailer, target vs Achievement) |  | Uday | NOT START
5 | FR 1 | 1 | Data Process | • Limited features of RSO App | if Click to visit(plan, visited, memo), Critical Retailer (Topup, SIM, eSAF) RSO wise count will be shown |  | Arif | NOT START
6 | FR 1 | 1 | Web API | • Limited features of RSO App | if Click to visit(plan, visited, memo), Critical Retailer (Topup, SIM, eSAF) RSO wise count will be shown |  | Uday | NOT START
7 | FR 1 | 1 | APK | • Limited features of RSO App | if Click to visit(plan, visited, memo), Critical Retailer (Topup, SIM, eSAF) RSO wise count will be shown |  | Asif | NOT START
8 | FR 1 | 1 | Web | Modality (Current offer and Comission stracture: type: RSO, M, DD, SUP) | in Web part target for field will modify as RSO, M, DD, Supervisor and in APP Current offer and Commission Struct will be display as per user type |  | Shakib | WORKING
9 | FR 1 | 1 | Web API | Modality (same RSO, Current offer and Comission stracture: type: RSO, M, DD, SUP) | in Web part target for field will modify as RSO, M, DD, Supervisor and in APP Current offer and Commission Struct will be display as per user type |  | Uday | WORKING
10 | FR 1 | 1 | Database | Monitoring | Monitoring (AD Hoc Report) |  | Arif | WORKING
11 | FR 1 | 1 | Data Process | Monitoring | Monitoring (Target vs Ach, top-bottom Seller, Route performance) |  | Arif | WORKING
12 | FR 1 | 1 | Web API | Active RSO List (New Menu for DD) | • Active RSO List : RSO Name, RSO Code, SR number, Route Count with search option (RSO code and Sr number search) (single search box) |  | Uday | WORKING
13 | FR 1 | 1 | APK | Active RSO List (New Menu for DD) | • Active RSO List : RSO Name, RSO Code, SR number, Route Count with search option (RSO code and Sr number search) (single search box) |  | Asif | NOT START
14 | FR 1 | 1 | Web API | • EV return (New Menu for DD) List view | RSO will make EV return request from Apps, Distributor will receive the return from apps |  |  | WORKING
15 | FR 1 | 1 | APK | • EV return (New Menu for DD) List view | RSO will make EV return request from Apps, Distributor will receive the return from apps |  | Asif | NOT START
16 | FR 1 | 1 | Web API | • EV return (button in List) by request ID | Return request details by request ID |  |  | WORKING
17 | FR 1 | 1 | APK | • EV return input form for Approve or reject request | Return request details information by request ID |  | Asif | NOT START
18 | FR 1 | 1 | Web API | • EV return to update request status by DD | • EV return to update request status by DD (Amount can be modify by DD and Source of Approve like : APP, Web) |  |  | WORKING
19 | FR 1 | 1 | APK | • EV return to update request status by DD | • EV return to update request status by DD (Amount can be modify by DD and Source of Approve like : APP, Web) |  | Asif | NOT START
20 | FR 1 | 1 | Data Process | • Reports (Monitoring) Select from drop down SIM/ I’top-up / SC Format (BRS doc) | • Reports (Monitoring) Select from drop down SIM/ I’top-up / SC Format (BRS doc) |  | Aawlad | WORKING
21 | FR 1 | 1 | Web API | • Reports (Monitoring) Select from drop down SIM/ I’top-up / SC Format (BRS doc) | • Reports (Monitoring) Select from drop down SIM/ I’top-up / SC Format (BRS doc) |  | Uday | WORKING
22 | FR 1 | 1 | APK | • Reports (Monitoring) Select from drop down SIM/ I’top-up / SC Format (BRS doc) | • Reports (Monitoring) Select from drop down SIM/ I’top-up / SC Format (BRS doc) |  | Asif | NOT START
23 | FR 1 | 1 | Data Process | Inventory: SIM / SC / Device Format: Product code, Product name, Count (current balance) | Inventory: SIM / SC / Device Format: Product code, Product name, Count (current balance) |  | Arif | WORKING
24 | FR 1 | 1 | Web API | Inventory: SIM / SC / Device Format: Product code, Product name, Count (current balance) | Inventory: SIM / SC / Device Format: Product code, Product name, Count (current balance) |  | Uday | WORKING
25 | FR 1 | 1 | APK | Inventory: SIM / SC / Device Format: Product code, Product name, Count (current balance) | Inventory: SIM / SC / Device Format: Product code, Product name, Count (current balance) |  | Asif | NOT START
26 | FR 1 | 1 | Data Process | Active Resource (format in BRS doc | Active Resources: (As like as DMS dashboard D-1) |  | Arif | WORKING
27 | FR 1 | 1 | Web API | Active Resource | Active Resources: (As like as DMS dashboard D-1) |  | Uday | WORKING
28 | FR 1 | 1 | APK | Active Resource | Active Resources: (As like as DMS dashboard D-1) |  | Asif | NOT START
29 | FR 1 | 1 | Data Process | o RSO wise Performance reports (Format in BRS doc) | (KPI: Prepaid Activation, EV Lifting, RSO Mixed Bundle, Data Pack, Voice Bundle) (As like DMS, need to overview DMS) |  | Arif | WORKING
30 | FR 1 | 1 | Web API | o RSO wise Performance reports | (KPI: Prepaid Activation, EV Lifting, RSO Mixed Bundle, Data Pack, Voice Bundle) (As like DMS, need to overview DMS) |  | Uday | WORKING
31 | FR 1 | 1 | APK | o RSO wise Performance reports | (KPI: Prepaid Activation, EV Lifting, RSO Mixed Bundle, Data Pack, Voice Bundle) (As like DMS, need to overview DMS) |  | Asif | NOT START
32 | FR 1 | 1 | Data Process | o Site: (D-1 format in BRS doc) | o Site: (D-1 format in BRS doc) |  | Arif | WORKING
33 | FR 1 | 1 | Web API | o Site: (D-1 format in BRS doc) | o Site: (D-1 format in BRS doc) |  |  | WORKING
34 | FR 1 | 1 | APK | o Site: (D-1 format in BRS doc) | o Site: (D-1 format in BRS doc) |  | Asif | NOT START
35 | FR 26 | 26 | Web API | Automated Birthday greetings | Automated Birthday greetings as flash popup (birthday card) Birthday update (Flash POP up) |  |  | NOT START
36 | FR 26 | 26 | APK | Automated Birthday greetings | Automated Birthday greetings as flash popup (birthday card) Birthday update (Flash POP up) |  | Asif | NOT START
37 | FR 26 | 26 | Web API | Weather update | Weather update as notification (synch with weather sites) |  |  | NOT START
38 | FR 26 | 26 | APK | Weather update | Weather update as notification (synch with weather sites) |  | Asif | NOT START
39 | FR 26 | 26 | Web API | Traffic update | Traffic update as notification (synch with Google Maps) |  |  | NOT START
40 | FR 26 | 26 | APK | Traffic update | Traffic update as notification (synch with Google Maps) |  | Asif | NOT START
41 | FR 25 | 25 | Web API | Include Profile picture option in App | Include Profile picture option in App |  |  | NOT START
42 | FR 25 | 25 | APK | Include Profile picture option in App | Include Profile picture option in App |  | Asif | NOT START
43 | FR 24 | 24 | Web | Distributor and BTS location point in Map |  |  |  | NOT START
44 | FR 24 | 24 | Web | Introduce distance scale in Map | Introduce distance scale in Map to check distance of any 2 points, i.e. bts to distributor, bts to retailer, bts to checkin/out point of rso (Lat-long and distance capture in report) |  |  | NOT START
45 | FR 24 | 24 | Web | In MAP excel export new fields Lat long , site, distance of entities | In MAP excel export new fields Lat long , site, distance of entities |  |  | NOT START
46 | FR 23 | 23 | APK | Existing feature where new development required | 2. Device Registration Date include, Handset Model OS Version |  | Asif | NOT START
47 | FR 23 | 23 | Web API | Existing feature where new development required | 2. Device Registration Date include, Handset Model OS Version |  |  | NOT START
48 | FR 23 | 23 | Web | Existing feature where new development required | 2. Device Registration Date include, Handset Model OS Version |  |  | NOT START
49 | FR 23 | 23 | APK | Existing feature where new development required | 3. From Complaint menu can be exit without checkout |  | Asif | NOT START
50 | FR 23 | 23 | Data Process | Existing feature where new development required | 1. RSO Target Vs Achievement (Al |  |  | NOT START
51 | FR 23 | 23 | Web API | Existing feature where new development required | 1. RSO Target Vs Achievement (Al |  |  | NOT START
52 | FR 23 | 23 | APK | Existing feature where new development required | 1. RSO Target Vs Achievement (Al |  | Asif | NOT START
53 | FR 22 | 22 | APK | Loader include | No Loader used which impact during big size picture |  | Asif | NOT START
54 | FR 19 | 19 | APK | QR Code in visit Retailer | Add new menu to read QR code and checking |  | Asif | NOT START
55 | FR 19 | 19 | Web API | QR Code in visit Retailer | checking from new menu QR code Read |  |  | NOT START
56 | FR 8 | 8 | APK | Revamp retailer Info Update | Add new field in APK to update Retailer info |  |  | NOT START
57 | FR 8 | 8 | Web API | Revamp retailer Info Update | save retailer update information request |  |  | NOT START
58 | FR 8 | 8 | Web | Revamp retailer Info Update (DMS) | Show the pending list of retailer edit information |  |  | DEVELOPMENT DONE
59 | FR 8 | 8 | Web | Revamp retailer Info Update (DMS) | Approve the pending list with effect on retailer table and retailerverification table with approve status |  |  | DEVELOPMENT DONE
60 | FR 11 | 11 | Web API | PIN less Child balance for RSO | Update topup retailer information API to get Retailer balance from EV |  | Mamun | WORKING
61 | FR 12 | 12 | Web API | Retailer EV PIN Unbar | Get the list of active LSO retailer |  | Uday | UAT FEEDBACK INC
62 | FR 12 | 12 | APK | Retailer EV PIN Unbar | Show the list of active LSO retailer with filter option |  | Asif | UAT FEEDBACK INC
63 | FR 12 | 12 | Web API | Retailer EV PIN Unbar | Call EV API to BAR or Unbar retailer with log history |  | Uday | UAT FEEDBACK INC
64 | FR 12 | 12 | APK | Retailer EV PIN Unbar (Request log) | Call EV API to BAR or Unbar retailer with log history |  | Asif | READY FOR UAT
65 | FR 12 | 12 | Web | Retailer EV PIN Unbar (Request log) | Get the list of active RSO |  | Uday | UAT FEEDBACK INC
66 | FR 12 | 12 | Web | Retailer EV PIN Unbar (Request log) | give permission RSO to do BAR or Unbar Retiler |  | Uday | UAT FEEDBACK INC
67 | FR 12 | 12 | Web API | Retailer EV PIN Unbar (Request log) | List of request status |  | Uday | WORKING
68 |  |  | APK | Retailer EV PIN Unbar (Request log) | List of request status |  | Asif | NOT START
69 | FR 13 | 13 | Web API only | Retailer EV PIN Reset (2-step) | Receive PIN reset request form Retailer APP |  |  | NOT START
70 | FR 13 | 13 | Web API | Retailer EV PIN Reset (2-step) | get the list of pending pin reset request |  |  | NOT START
71 | FR 13 | 13 | APK | Retailer EV PIN Reset (2-step) | Show the list of pending pin reset request |  |  | NOT START
72 | FR 13 | 13 | Web API | Retailer EV PIN Reset (2-step) (Request log) | Call EV API and update with EV API Response |  |  | NOT START
73 | FR 13 | 13 | Web API | Retailer EV PIN Reset (2-step) (Request log) | Update Request status to retaieler APP |  |  | NOT START
74 | FR 15 | 15 | Web | Low balance retailer definition from Excel upload | Critical Retailer excel upload slowness (3lac +) |  |  | NOT START
75 | FR 19 | 19 | Web API | QR Code in visit Retailer | QR Code in visit plan and include visit plan page in Menu |  |  | NOT START
76 | FR 19 | 19 | APK | QR Code in visit Retailer | QR Code in visit plan and include visit plan page in Menu |  | Asif | NOT START
77 | FR 22 | 22 | APK | No Loader used which impact during big size picture | No Loader used which impact during big size picture |  | Asif | NOT START
78 | FR 25 | 25 | APK | Include Profile picture option in App |  |  | Asif | NOT START
79 | FR 26 | 26 | Web API | Automated Birthday greetings as flash popup |  |  |  | NOT START
80 | FR 26 | 26 | Data Process | Automated Birthday greetings as flash popup |  |  |  | NOT START
81 | FR 26 | 26 | Web API | Weather update as notification |  |  |  | NOT START
82 | FR 26 | 26 | APK | Weather update as notification |  |  | Asif | NOT START
83 | FR 26 | 26 | Data Process | Weather update as notification |  |  |  | NOT START
84 | FR 26 | 26 | Web API | Weather update as notification |  |  |  | NOT START
85 | FR 26 | 26 | APK | Weather update as notification |  |  | Asif | NOT START
86 | FR 26 | 26 | Data Process | Weather update as notification |  |  |  | NOT START
87 | FR 26 | 26 | Web API | Traffic update as notification (synch with Google Maps) |  |  |  | NOT START
88 | FR 26 | 26 | APK | Traffic update as notification (synch with Google Maps) |  |  | Asif | NOT START
89 | FR 26 | 26 | Data Process | Traffic update as notification (synch with Google Maps) |  |  |  | NOT START
90 | FR 31 | 31 | Web API | Bottom 10 Low Performing Site details | Get Bottom 10 Low performing site for MTL and LMTD |  |  | NOT START
91 | FR 31 | 31 | APK | Bottom 10 Low Performing Site details | View the list of 10 Low performing site in APP |  | Asif | NOT START
92 | FR 31 | 31 | Data Process | Bottom 10 Low Performing Site details | Data process for MTD |  |  | NOT START
93 | FR 31 | 31 | Data Process | Bottom 10 Low Performing Site details | Data process for LMTD |  |  | NOT START
94 | FR 31 | 31 | Data Process | SRAN BI integration for report view |  |  |  | NOT START |  |  | BI
95 | FR 31 | 31 | Web API | SRAN BI integration for report view |  |  |  | NOT START
96 | FR 31 | 31 | APK | SRAN BI integration for report view |  |  |  | NOT START
97 | FR 30 | 30 | Data Process | Today’s sales RSO apps and Total | Send message data process |  |  | NOT START
98 | FR 30 | 30 | Web | Today’s sales RSO apps and Total | add New Web UI to display report |  |  | NOT START
99 | FR 28 | 28 | Web API only | Banner View from retailer App | Exclude |  |  | DEPENDENCY ITEM |  |  | Retailer App
100 | FR 10 | 10 | Web API only | Retailer complaint to VFocus | Share API with Retailer app to save complain request |  | Uday | DEVELOPMENT DONE |  |  | Retailer App
101 | FR 10 | 10 | Web API | Retailer complaint to VFocus | Get the complain list |  | Uday | DEVELOPMENT DONE
102 | FR 10 | 10 | APK | Retailer complaint to VFocus | Show the list of complain in APP, with approve button |  | Asif | NOT START
103 | FR 10 | 10 | Web API | Retailer complaint to VFocus | Update complain with feedback and status |  | Uday | DEVELOPMENT DONE |  |  | Retailer App
104 | FR 10 | 10 | Web API only | Retailer complaint to VFocus | Call Retailer APP API to update status |  | Uday | WORKING
105 | FR 2 | 2 | Database | RSO Payment Acknowledgement by SMS | After uploading salary Payment acknowledgement |  |  | NOT START
106 | FR 2 | 2 | Web | RSO Payment Acknowledgement (modify) | Modify with extra column (status=>pending, Read, AK: Complain=>Y/N :AK date, Receive date, Complain type, AK S) |  | Shakib | DEVELOPMENT DONE
107 | FR 2 | 2 | Web API | Get RSO Salary (modify with extra column) |  |  | Uday | DEVELOPMENT DONE
108 | FR 2 | 2 | APK | Get RSO Salary (modify with extra column and AK button) |  |  | Asif | DEVELOPMENT DONE
109 | FR 2 | 2 | APK | Develop AK form | Complain --yes/No, if No Receive date field will be enable |  | Asif | DEVELOPMENT DONE
110 | FR 2 | 2 | Web API | Get AK status | Get AK status(salary not received, received less, received very late, Others) |  | Uday | DEVELOPMENT DONE
111 | FR 2 | 2 | Web API | Save AK information from RSO APP |  |  | Uday | DEVELOPMENT DONE
112 | FR 3 | 3 | Database | IF target not uploaded CM target = LM target and CM Ach | add LM target as CM target |  | Mamun | READY FOR UAT
113 | FR 3 | 3 | Web | IF target not uploaded CM target = LM target and CM Ach | Delete from target if LM |  | Mamun | READY FOR UAT
114 | FR 4 | 4 | Web | Lat-Long of retailer, Distributor (Save) | upload Distributor code, Address, lat and long from admin |  | Shakib | DEVELOPMENT DONE
115 | FR 4 | 4 | Web | Lat-Long of retailer, Distributor (Display) | upload Distributor code, Address, lat and long from admin |  | Shakib | DEVELOPMENT DONE
116 | FR 4 | 4 | Web | Lat-Long of retailer, Retailer (Save) | upload Retailer code, Address, lat and long from admin |  | Shakib | DEVELOPMENT DONE
117 | FR 4 | 4 | Web | Lat-Long of retailer, Retailer (Display) | upload Retailer code, Address, lat and long from admin |  | Shakib | DEVELOPMENT DONE
118 | FR 4 | 4 | Web | Lat-Long of retailer, Retailer ZM | Pending list for ZAM approval with map view |  | Shakib | DEVELOPMENT DONE
119 | FR 4 | 4 | Web | Lat-Long of retailer, Retailer ZM | Pending list for ZAM approval with map view |  | Shakib | DEVELOPMENT DONE
120 | FR 4 | 4 | Web | Lat-Long information update • Report |  |  | Shakib | NOT START
121 | FR 6 | 6 | APK | UI / UX change as per MyBL App / Retailer App |  |  | Asif | WORKING
122 | FR 7 | 7 | Database | Login credentials as per dms Supervisor | Login credentials as per dms (Supervisor , Supervisor code) |  |  | NOT START
123 | FR 29 | 29 | Data Process | Top – Bottom performing Retailer | LM and CM till date (D-1) |  |  | NOT START
124 | FR 29 | 29 | Data Process | Top – Bottom performing Retailer | Top 5 SSO : SIM Activation |  |  | NOT START
125 | FR 29 | 29 | Data Process | Top – Bottom performing Retailer | TOP 5 LSO |  |  | NOT START
126 | FR 29 | 29 | Data Process | Top – Bottom performing Retailer | Bottom 5 SSO |  |  | NOT START
127 | FR 29 | 29 | Data Process | Top – Bottom performing Retailer | Bottom 10 LSO (C2S) |  |  | NOT START
128 | FR 29 | 29 | APK | Top – Bottom performing Retailer | LM and CM till date (D-1) |  |  | NOT START
129 | FR 29 | 29 | APK | Top – Bottom performing Retailer | Top 5 SSO : SIM Activation |  |  | NOT START
130 | FR 29 | 29 | APK | Top – Bottom performing Retailer | TOP 5 LSO |  |  | NOT START
131 | FR 29 | 29 | APK | Top – Bottom performing Retailer | Bottom 5 SSO |  |  | NOT START
132 | FR 29 | 29 | APK | Top – Bottom performing Retailer | Bottom 10 LSO (C2S) |  |  | NOT START
133 | FR 29 | 29 | Web API | Top – Bottom performing Retailer | LM and CM till date (D-1) |  |  | WORKING
134 | FR 29 | 29 | Web API | Top – Bottom performing Retailer | Top 5 SSO : SIM Activation |  |  | WORKING
135 | FR 29 | 29 | Web API | Top – Bottom performing Retailer | TOP 5 LSO |  |  | WORKING
136 | FR 29 | 29 | Web API | Top – Bottom performing Retailer | Bottom 5 SSO |  |  | WORKING
137 | FR 29 | 29 | Web API | Top – Bottom performing Retailer | Bottom 10 LSO (C2S) |  |  | WORKING
138 | FR 29 | 29 | Web API | RSO earning | select RSO, select Month Headwise RSO income (Fixed Salary, Commission, Incentive) |  |  | NOT START
139 | FR 29 | 29 | APK | RSO earning | select RSO, select Month Headwise RSO income (Fixed Salary, Commission, Incentive) |  |  | NOT START
140 | FR 29 | 29 | APK | SSO and LSO Critical retailer count | SSO and LSO Critical retailer count, service provided to critical retailer: live integration |  |  | NOT START
141 | FR 29 | 29 | Web API | SSO and LSO Critical retailer count | SSO and LSO Critical retailer count, service provided to critical retailer: live integration |  |  | NOT START
142 | FR 29 | 29 | Web API | Critical balance | List of Critical Retailer of RSO |  |  | NOT START
143 | FR 29 | 29 | APK | Critical balance | List of Critical Retailer of RSO |  |  | NOT START
144 | FR 29 | 29 | Web | Current offer and Campaign section integration from RSO App web | Upload campaing data |  |  | WORKING
145 | FR 29 | 29 | Web API | Current offer and Campaign section integration from RSO App web | Use current RSO API |  |  | NOT START
146 | FR 29 | 29 | APK | Current offer and Campaign section integration from RSO App web | Use current RSO API |  |  | NOT START
147 | FR 29 | 29 | Web API | View of commission, Current offers and Campaigns as of RSO App | Use current RSO API |  |  | NOT START
148 | FR 29 | 29 | APK | View of commission, Current offers and Campaigns as of RSO App | Use current RSO API |  |  | NOT START
149 | FR 21 | 21 | Web API | Retailer Demand to RSO App | Save Retailer demand from Retailer APP |  |  | NOT START
150 | FR 21 | 21 | Web API | Retailer Demand to RSO App | List of Retailer demand |  |  | NOT START
151 | FR 21 | 21 | APK | Retailer Demand to RSO App | List of Retailer demand |  |  | NOT START
152 | FR 21 | 21 | Web API | Retailer Demand to RSO App | Issue Product to retailer form demand list |  |  | NOT START
153 | FR 21 | 21 | Data Process | Retailer Demand to RSO App | Issue Product to retailer form demand list (checking, Qty pass, issue status…) |  |  | NOT START
154 | FR 21 | 21 | Web API only |  | Call Retailer APP API to update status |  |  | NOT START
155 | FR 18 | 18 | Web API | Separate I’top-up module | Call EV API to get RSO current balance |  |  | NOT START
156 | FR 18 | 18 | Web API | Separate I’top-up module | Get list of LSO Retailer |  |  | NOT START
157 | FR 18 | 18 | Web API | Separate I’top-up module | Checkin to retailer and land to retailer itopup page |  |  | NOT START
158 | FR 18 | 18 | APK | Separate I’top-up module | Checkin to retailer and land to retailer itopup page |  |  | NOT START
159 | FR 18 | 18 | Web API | Separate I’top-up module | Save itopup transfer request |  |  | NOT START
160 | FR 18 | 18 | Web API | Separate I’top-up module | Checkout from retailer panel |  |  | NOT START
161 | FR 14 | 14 | Web API | Live C2C and C2S with time mentioned | Today’s Sales report will be updated with Live C2C (APP & barphone) |  | Mamun | WORKING
162 | FR 14 | 14 | APK | Live C2C and C2S with time mentioned | Today’s Sales report will be updated with Live C2C (APP & barphone) |  | Asif | NOT START
163 | FR 14 | 14 | Web API | Live C2C and C2S with time mentioned | Today’s Target Vs Sold will capture both through App & barphone |  |  | NOT START
164 | FR 14 | 14 | APK | Live C2C and C2S with time mentioned | Today’s Target Vs Sold will capture both through App & barphone |  | Asif | NOT START
165 | FR 14 | 14 | Web API | Live C2C and C2S with time mentioned | I’top-up Target vs achievement updated with Live C2S (new colour for todays achievement |  |  | NOT START
166 | FR 14 | 14 | APK | Live C2C and C2S with time mentioned | I’top-up Target vs achievement updated with Live C2S (new colour for todays achievement |  | Asif | NOT START
167 | FR 14 | 14 | Web API | Live C2C and C2S with time mentioned | SIM Target vs achievement updated with Live Biometric |  |  | NOT START
168 | FR 14 | 14 | APK | Live C2C and C2S with time mentioned | SIM Target vs achievement updated with Live Biometric |  | Asif | NOT START
169 | FR 14 | 14 | Data Process | Live C2C and C2S with time mentioned | Live C2S will be used to identify Critical retailers |  |  | NOT START
170 | FR 14 | 14 | Web API | Live C2C and C2S with time mentioned | Live retailer balance in i’top-up section of retailer dashboard |  |  | NOT START
171 | FR 14 | 14 | APK | Live C2C and C2S with time mentioned | Live retailer balance in i’top-up section of retailer dashboard |  | Asif | NOT START
172 | FR 5 | 5 | Data Process | Merchandiser App revamp | Device Registration (Merchandiser login with new password policy and Merchandiser number) |  |  | NOT START
173 | FR 5 | 5 | Web API | Merchandiser App revamp | Device Registration (Merchandiser login with new password policy and Merchandiser number) |  |  | NOT START
174 | FR 5 | 5 | APK | Merchandiser App revamp | Device Registration (Merchandiser login with new password policy and Merchandiser number) |  |  | NOT START
175 | FR 5 | 5 | Web API | Merchandiser App revamp | Customized Notification for Merchandiser |  |  | NOT START
176 | FR 5 | 5 | APK | Merchandiser App revamp | Customized Notification for Merchandiser |  |  | NOT START
177 | FR 5 | 5 | Web API | Merchandiser App revamp | Customized Popup for Merchandiser |  |  | NOT START
178 | FR 5 | 5 | APK | Merchandiser App revamp | Customized Popup for Merchandiser |  |  | NOT START
179 | FR 5 | 5 | Web API | Merchandiser App revamp | Customized Scroll for Merchandiser |  |  | NOT START
180 | FR 5 | 5 | APK | Merchandiser App revamp | Customized Scroll for Merchandiser |  |  | NOT START
181 | FR 5 | 5 | Web | Merchandiser App revamp | Target vs Achievement (web as like as RSO target upload & list view) |  |  | NOT START
182 | FR 5 | 5 | Web API | Merchandiser App revamp | Target vs Achievement As like as RSO |  |  | NOT START
183 | FR 5 | 5 | APK | Merchandiser App revamp | Target vs Achievement As like as RSO (prograsebar) |  |  | NOT START
184 | FR 5 | 5 | Web API | Merchandiser App revamp | Stock add |  |  | NOT START
185 | FR 5 | 5 | APK | Merchandiser App revamp | Stock add |  |  | NOT START
186 | FR 5 | 5 | Web API | Merchandiser App revamp | Stock list view |  |  | NOT START
187 | FR 5 | 5 | APK | Merchandiser App revamp | Stock list view |  |  | NOT START
188 | FR 5 | 5 | Web API | Merchandiser App revamp | issue from stock |  |  | NOT START
189 | FR 5 | 5 | APK | Merchandiser App revamp | issue from stock |  |  | NOT START
190 | FR 5 | 5 | Web | Merchandiser App revamp | Stock report as like as RSO daily stock report |  |  | NOT START
191 | FR 5 | 5 | Web API | Merchandiser App revamp | Retailer checking from QR |  |  | NOT START
192 | FR 5 | 5 | APK | Merchandiser App revamp | Retailer checking from QR |  |  | NOT START
193 | FR 5 | 5 | Web API | Merchandiser App revamp | Dismantling list add |  |  | NOT START
194 | FR 5 | 5 | APK | Merchandiser App revamp | Dismantling list add |  |  | NOT START
195 | FR 5 | 5 | Web API | Merchandiser App revamp | Dismantling list with retailer info |  |  | NOT START
196 | FR 5 | 5 | APK | Merchandiser App revamp | Dismantling list with retailer info |  |  | NOT START
197 | FR 5 | 5 | Web API | Merchandiser App revamp | Return Material from Retailer Add |  |  | NOT START
198 | FR 5 | 5 | APK | Merchandiser App revamp | Return Material from Retailer Add |  |  | NOT START
199 | FR 20 | 20 | No Task | Resize Routes section in Routes List page | Exclude |  |  | DEPENDENCY ITEM
200 | FR 27 | 27 | No Task | Resize Routes section in Routes List page | Exclude |  |  | DEPENDENCY ITEM
201 | FR 32 | 32 | Web | Notic boad | Upload notic board information |  |  | NOT START
202 | FR 32 | 32 | Web API | Notic boad | List of Notic board |  |  | NOT START
203 | FR 32 | 32 | APK | Notic boad | List of Notic board |  |  | NOT START

## Delivery Plan
Application | FR wise Task No | Development is on going | Development pending | Pending for business | Dependency Items | Ready for UAT | UAT Feedback | Ready for live
Incorporation
DMS | 29 | [7 empty] | RSO
RSO App | 28 | 5 | 23 | [5 empty] | Delivery Date | FR NO | Total
4
3
3
3
3
4
3
3
2
[9 empty] | Total |  | 28
[9 empty] | 2021-07-31 |  | 15:00

## APP Menu List
RSO |  |  | MERCHANDISER
SL | Level 1 | Level 2 | SL | L1 | L2
1 | SALES & STOCK | STOCK | 1 | DASHBOARD
1 | SALES & STOCK | SR BALANCE | 2 | ROUTES
2 | DASHBOARD |  | 3 | ISSUE POSM TO RETAILER
3 | ROUTES |  | 4 | NOTIFICATION
4 | CRITICAL | CRITICAL RETAILERS | 5 | MODALITY | CURRENT OFFERS
4 | CRITICAL | RETAILER'S DEMAND | 6 | MODALITY | COMISSION STRUCTURES
5 | MODALITY | CURRENT OFFERS | 7 | FEEDBACK TOOLS | MARKET UPDATE
5 | MODALITY | COMMISSION STRUCTURES | 8 | FEEDBACK TOOLS | SURVEY
5 | MODALITY | CAMPAIGN | 9 | SKILL DEVELOPMENT | FAQ
6 | TRANSACTION | TODAY'S SALES REPORT | 10 | SKILL DEVELOPMENT | TRAINING
6 | TRANSACTION | TOPUP HISTORY | 11 | LOG OUT
7 | MONITORING | TARGET VS ACHIEVEMENT
7 | MONITORING | ROUTE PERFORMANCE
7 | MONITORING | TOP-BOTTOM SELLER
8 | AID TOOL | SIM STATUS CHECK
8 | AID TOOL | RETURN MEMO
9 | FEEDBACK TOOLS | MARKET UPDATE
9 | FEEDBACK TOOLS | SURVEY
10 | EARNING | RSO EARNING
10 | EARNING | RSO COMISSION SUMMARY
11 | SKILL DEVELOPMENT | TRAINING
11 | SKILL DEVELOPMENT | BEST PRACTICES
11 | SKILL DEVELOPMENT | RETAILER BEST PRACTICES
11 | SKILL DEVELOPMENT | FAQ
12 | LOG OUT
NEW OUTLET REGISTRATION

## QA Status & Bug Repo (App+Web)
| SL. | Status | FR | SRS | App/Web | Bug | Ready for UAT | Responsibility |  |  | UAT Plan |  |  | UAT Conducted
| 1 | Passed | FR 2 | SRS page23 | Web | RSO Salary Excel Upload stucks at 70% and not working. |  |  |  | 1 | FR-2, FR-3, FR 4, FR-6, FR-8, FR 10, FR 11, FR 12, FR 13, FR 17, FR 21, FR 22, FR 23, FR 24, FR 25 | Vs | Day-1 | FR 2, FR 3, FR 4, FR 6, FR 8, FR 10, FR 11, FR 12, FR 13, FR 17, FR 20, FR 21, FR 22, FR 23, FR 24 | Issue/Bug UAT D1 | Count
| 2 | Passed | FR 2 | SRS page23 | Web | Need UI change for "Acknowledgement Type" Filter Feature with options (Salary Not Received, Received Less, Received Very Late, Others) |  |  |  | 2 | FR-1, FR 5, FR 7, FR 9, FR 14, FR 15, FR 16, FR 18, FR 19, FR 20, FR 26, FR 27, FR 28, FR 29, FR 30 |  | Day-2 | FR 1, FR 5, FR 7, FR 9, FR 14, FR 15, FR 16, FR 18, FR 19, FR 25, FR 26, FR 27, FR 28, FR 29, FR 30 | Web Side
| 3 | Passed | FR 2 | SRS page23 | Web | Need RSO Salary Report with New fields (Acknowledgement Type, and Acknowledgement Details) |  | Shakib | [6 empty] | App Side
| 4 | Passed | FR 2 | SRS page 25 | App Dependency on Web | After giving RSO Salary Acknowledgement it's not saving and not showing on the Web and in App |  | Mamun
| 5 |  | FR 2 | SRS page 25 | App | There is no option in SRS/App/Web about "Salary Received Properly" as RSO Acknowledgement for RSO |  | Mamun
| 6 | Done Passed (Nahid) | FR 2 | SRS page 25 | App | The Complain Details" and "Complain Type" must be editable/usable only when the "Complain" Radio button is enabled. |  | Abdullah+mamu
| 7 | Passed | FR 3 | SRS page 26 | App | RSO Target Vs Achievement for Current Month, If the Current Month's Achievement data is not available then Show the Last Month's Target Vs Achievement data must be shown with different color or marked as Last Month's Achievement Data is not showing.
| 8 | Mamun vaia | FR 4 |  | Web | On the "Distributor GPS Update Approval" the distributor old lat-long data shows 0 (Zero) after uploading and approving it twice.
| 9 | Development Pending from Web & APP. Tomorrow it will be fixed: Responsible Ifteraz/Mamun/Awlad | FR 8 | SRS page 65, 66 | Web | Adding 3 new fields (NID, TIN, Trade License) on the RSO App View in Retailer Info Update, and Need to test the Info update Approval goes in DMS works.
| 10 | Passed | FR 10 | SRS page 70 | Web+App | RSO Salary Complain does not save and does not view for ZM, On the Retailer Complain List After Clicking on a complain in the "Status" dropdwon more option needed like Escaleted To ZM ***
| 11 | Passed | FR 11 | SRS page 73 | App | Need Valid Data (Itop-up Balance) for a retailer to check the Itop-up Transfer.
|  |  | FR 12 |  | App | Ev Pin Bar-Unbar UI and Function not appropriate and not successfull
| 12 | Closed | FR 12 | SRS page 76 | App | On the EV Pin Unbar Request page there must be Filters: (All, Barred, Unbarred) on the Top of the page, For every Retailer, Status (Pending or Completed) and (Barred or Unbarred) with Green or Red color must show appropriately, For every Retailer, Request Time and Response Time must show appropriately, Need Valid Data for Retailers to check the Bar-Unbar feature. |  | Asif
| 13 | Passed Done R063574 | FR 13 | SRS page 79 | App | Need Valid Data for Retailers to check the 2 steps PIN Reset Feature.
| 14 | Passed | FR 17 | SRS page 85 | Web | Need Valid Data for Retailers to check the Retailer Location/Distance wise sorting for RSO Visit
| 15 | Passed Need to find some sample data for UAT | FR 21 | SRS page 91 | Web + App | Loader in All Image place , Need to Know Logic
| 16 | Passed | FR 22 | SRS page 91 | App | RSO Target Vs Achievement (Need Achievement Data), From Complaint menu can be exit without checkout Not Working, Retailer's created complains do not show in Retailer Complain List.
| 17 | Passed | FR 23 | SRS page 91 | Web | RSO Footsteps View Excel Export does not work. |  | Mamun vaia
UAT D2 | 1 | Passed | FR 1 | SRS page 6, 7, 8 | App | 1. Need Valid data for Distributor Users in App Dashboard. 2. App- In Memo menu Dashboard showing Zero (0) data, but inside showing memo data. | RAJJOY01
| 2 |  | FR 5 | SRS page 31, 32 | App | 1. Need Merchandiser's credintials to check the process. 2. Need Merchandiser's Test Data for Dashboard.
| 3 | Done (Jesy) Passed (Nahid) | FR 5 | SRS page 33 | Web | On the page "Add New Notice" for Merchandiser, Template Excel RSO and Template Excel Merchandiser download do not work.
|  | Done (Jesy) Passed (Nahid) | FR 5 | SRS page 33 | Web | On the page "Add New Notice" for Merchandiser, after selecting "Notification For :" Merchandisers the excel upload file name should be more appropriate. (Error for Merchandiser, and Supervisor)
| 4 |  | FR 7 | SRS page 50-64 | App | 1. Need Supervisor's credintials to check the process. 2. Supervisor's Message, Ticker, Flash Notification not showing in App
| 5 | Passed Locally Working | FR 7 | SRS page 63-64 | Web | Merchandiser Point Creation.
| 6 | Passed | FR 9 | SRS page 68, 70 | App | 1. Need ZM's credintials to check the process.
| 7 | Passed | FR 14 | SRS page 80 | App | Today’s Sales report will be updated with Live C2C (itopup App and barphone). Add remarks App / SIM Data are showing only for Itopup, Add remarks App / SIM Logic need to know
| 8 | Done (Jesy) Passed, Locally Working (Nahid) | FR 15 | SRS page 84 | Web | Retailer Critical Balance Upload does not work. (Excel Template)
| 9 |  | FR 16 | SRS page 85 | App | Need to know logic for, 1. Site location, Distributor location, retailer location in app 2. Automatically Detect Site and then view site info 3. Site View: BTS code, BTS Address, Site Type (2G+3G+4G), SSO retailer count, LSO retailer count, avg SIM sales, avg itopup sales. 4. This option for RSO, Merchandiser, Supervisor, Distributor
| 10 | Passed | FR 18 |  | App Successfull DB Not Successfull | 1. After Completing a Quick Recharge for for Retailer "R063574" (Golap Telecom) of 1001 Taka it did not hit or saved in the Database Top_Up_Issue Table. (Can be Job/Scheduler Issue)
| 11 |  | FR 19 | SRS page 88 | App | On the "Today's Highlights", In Visited menu the Retailer QR code Scan is not working
| 12 | Passed | FR 25 | SRS page 93, 94, 95 | Web + App | Need to check the "Happy Birthday" Notification for RSO Birth Date in App, after uploading the RSO Birth Data data in Web. (Need Job/Scheduler Execution)
q | 13 |  | FR 26 | SRS page 96 | Web + App | 1. There is no Campaign Creation page (UI) in the Web Module. (Passed) 2. There are no test data in Campaign page in App. 3. There are no page (UI) of Commission Structure to view the data in the App for RSO users. 4. After Creating a Current offer for Distributor it does not show in the App for Distributor User, and inappropriate same multiple data are showing. 5. After Creating Campaign in the web for RSO, and Distributor the data do not show in the App for RSO, and Distributor users. 6. There are no page (UI) of Commission Structure to view the data in the App for Distributor users. 7. After adding a "Commission Structure" for RSO, it does not show on the app for RSO user.
| 14 | Passed | FR 27 | SRS page 99 | Web | 1. Observation for pagination and Search feature on the "Today’s sales RSO by RSO" report page. (Nahid)
| 15 |  | FR 28 | SRS page 100 | App | 1. Site Report must have these fields (Site Code, SRAN, Address, Site type, Site on air date, Utilization (%) / recharge, SSO Count, LSO Count).
| 16 | Passed | FR 29 | SRS page 101 | Web | 1. Need to know the logic for Uploaded pdf file view, in the Creation of a Notice. (Same As Existing)
| 17 | Done (Jesy) Passed (Nahid) | FR 30 |  | Web | On the page "Update App Menu" after changing informations, the information do not gets updated.
UAT D3 | 19 |  | FR 30 | SRS 104 | App | 1. App side integration in-progress for App side menu/page hit by users.(solved) (Passed) 2. Web- On the Update after clicking on the edit the update button does not work appropriately. (solved Jesy) (Passed) 3. Web- On the Existing RSO Activity page After clicking on export without selecting any filter all data should be downloaded. (Passed) 4. Web- Need Valid data in the Rso Activity Log page and in Excel Export Report. (Passed) 5. Web- The Report must have the fields: (SL, Date, User Code, User Type, Feature Name, Hit Count). (Passed) | in-progress Report format need to modify |  | UAT Plan RSO App & Web
| 20 |  | FR 29 | SRS 101, 102 | App + Web | 1. App- Date Filter Needed in Notice Board. (solved) (Passed) 2. Web- JPEG type file need to be allowed On the New Notice Add. (solved Jesy) (passed) (Passed) 3. App- Uploaded JPEG file does not show in the app.(solved) (Passed) 4. Web + App- uploaded pdf file in web does not show in the app while creating a new notice.(solved) (Passed) 5. App- uploaded jpg/jpeg file in web does not show in the app while creating a new notice.(solved) (Passed) 6. Web- In a Notice if IsActive is unchecked the data must not show in the app. (Passed) | 1. Web- On the Add New Notice ISActive issue. |  | Day-3 | FR-30, FR-29, FR-28, FR-27, FR-19, FR-18, FR-15, FR-26, FR-16, FR 7, FR 9, FR-14, , FR-20
| 21 |  | FR 28 | SRS page 100 | App | 1. Site Report must have these fields (Site Code, SRAN, Address, Site type, Site on air date, Utilization (%) / recharge, SSO Count, LSO Count, SIM). (Passed) (for SRAN, SIM data column New Format will be provided by Banglalink BS Team) 2. App/Web Current Month - Last Month Data Logic of Bottom 10 Low Performing Site details data and view. | in-progress
| 22 |  | FR 27 | SRS page 99 | Web | 1. Web- Need Processed Data and process to check the Report data. (Passed) 2. Web- In the data table autometic scroll issue. (Pending) (Passed) (Need Decession from Ifteraz Vaia) 3. In the reports view a column need to include "Sold through App" and count data under it. (solved Jesy) (Passed) | in-progress
| 23 |  | FR 19 | SRS page 88 | App | 1. App- On the Visited List Retailer Cart does not have the Chek-in and Check-out time. (solved) (Passed) 2. App- After Visited a Retailer, After Check-out (Except Not A Visit) In the Visited Page the the visited retailer must be green color(solved) (Passed) 3. App- After completing an itop-up of a retailer which is not in the visit plan it does not appear on the Visited List. (Dependency on Web) (Passed) 4. App- On the Visited, Memo page there are no Date filter mentioned in the SRS/BRS. (solved) (passed) | Done
| 24 |  | FR 18 | SRS page 87 | App | 1. App- Need Update Visited and Memo section for the Quick Recharge of a Retailer.(solved) (Passed) 2. App- On the Visited List Retailer Cart does not have the Chek-in and Check-out time.(solved) (Passed) 3. App- On the Quick Recharge page "Scan" not working.(solved) (Passed) 4. App- Need View of Confirmation page with retailer number, code, Amount and Balance in Quick Recharge.(solved) (Passed) | Done
|  |  | FR 15 | SRS page 84 | Web | 1. Web- Need to check that Critical Retailer Upload can handle 3 lacs data entry. (Passed)
|  |  | FR 14 | SRS page 80 | App | 1. App- Need Valid/processed data to check the Today’s Sales report are updated with Live C2C data. (Dependency on Web) 2. App- Need Today’s Sales report data with time mentioned feature. (Dependency on Web) 3. App+Web- Need Valid Uploaded data on the web for Current Month Target. (Dependency on Web) 4. App- Need itopup, Today’s Target Vs Sold data are capturing both through App + Sim 6. App- Need Today’s Target Vs Sold data are capturing For Sim and SC (DMS + App). 7. App+Web- Need Retailer Panel Dashboard's processed test data.
|  |  | FR 16 | SRS page 85 | App | 1. App- Need valid data of mapping between RSO and Retailer, and Retailer to Sites, and those site (sites) are shown in the map.(solved) 2. Web- Need to Change the BTS Test Data Lat-Long and Address.
|  |  | FR 20 | SRS page 90 | App | 1. App- On the Retailer Panel, On the Product page In the Demand page need valid test data. (data list empty . check on post_man) 2. App+Web- Need Valid data of Retailers with Retailer Cart as same as SRS 3. App- Need to check if a demand request is pending Retailer can’t add a new request for same day. 5. App- Retailers Demand have the only status of (1 Pending 2. Receive 3. Delivered 4. Partial delivered 5. On the Way) only.
|  |  | FR 26 | SRS page 96 | App | 1. App- After uploading a Commission Structure in the web the uploaded data does not show in the app for RSO user.(data list empty . check on post_man) 2. Web- Need to know the data creation part of RSO Campaign in RSO App in The Web Module. (Passed) (Mamun Vai) 3. | 1. Need To Update Target Type Dropdown
Issue = 8 (FR 20 full), (FR 26 =2)
Data Dependency = 9 (FR 14 = 7)