## Sheet1
SL. | FR Number | UAT Feedback | Business Observation | Status
1 | FR 2 | 1. *APP- In RSO Earning for RSO login the *Remarks field must be not editable and only readable. 2. *Web- Acknowledgemnt Status should not be number, need specific words from BL Business team. 3. * Web- Slary Month, and Acknoledgement Type filter must be AND and OR both. 4. * Web- After Going to Show List Page the Loader shows in-appropriately on the top-middle of the page. 5. Web- After clicking on the show list without selecting any filter all data must show. 6. After Uploading Same Month & Different RSO File the Salary Period is showing same month multiple time. 7. App- After Submitting an Acknoledgement from RSO users in Salary Earning same data are showing multiple time in Complains for Distributors user. |  | Pending | UAT Plan RSO App & Web
2 | FR 3 | 1. * App View- Current Month, Last Month Data logic (Dependency on Web Target Upload) |  | Pending | Day-1 | FR 2, FR 3, FR 4, FR 6, FR 8, FR 10, FR 11, FR 12, FR 13, FR 17, FR 20, FR 21, FR 22, FR 23, FR 24
3 | FR 4 | 1. * Web- Distributor GPS Upload, after uploading the values 2 time for same DIstributor the Old Lat-Long remains Zero (0). |  | Pending | Day-2 | FR 1, FR 5, FR 7, FR 9, FR 14, FR 15, FR 16, FR 18, FR 19, FR 25, FR 26, FR 27, FR 28, FR 29, FR 30
4 | FR 6 | UAT Not Completed (Will be done Parallelly) |  | Pending
5 | FR 8 | 1. * App- Retailer Info Update Page, Error Message Issue (Something Went Erong..) 2. * App- Retailer Info Update options Mandatory/Non-Mandatory issue. 3. * App- New Ownshop Data Issue. 4. * App- NID, TL, TIN Saved data show issue in app. |  | Pending
6 | FR 10 | 1. *App- RSO type users must only view the *Remarks and can not Edit the *Remarks. |  | Pending
7 | FR 11 | 1. * App- In Route Page Search Filter Needed. | 1. (ADD Stock Real Time Data from EV, Business Observation). 2. *App- Need RSO Live Balance as "Your Balance" from EV (Business Observation) (Need Discussion ) | Pending
8 | FR 12 | No Feedback | No Feedback | Passed
9 | FR 13 | 1. *App- Reatiler Name Required in PIN Reset page. |  | Pending
10 | FR 17 | No Feedback | No Feedback | Passed
11 | FR 20 | 1. *App- On the Retailer Demand Page, The Product Information View Size must be re-sized to large for more appropriate view. |  | Pending
12 | FR 21 | No Feedback | (Need To check and Discuss more) | Passed
13 | FR 22 | 1. * RSO Target vs Acheivement Data need to complete the process. 2. * Device Registration need more discussion. 3. * From Complaint menu can not be exit without checkout. |  | 1.1 Pending 1.2 Passed 1.3 Failed
14 | FR 23 | 1. * Web- RSO Footsteps View, Need Selected Point Cancel option. 2. * Web- RSO Checkin, Chekout point Data. |  | Pending
15 | FR 24 | No Feedback | No Feedback | Passed
| FR 1 | 1. App- On the RSO Visitted page for each Retailer Checkin Time, Check Out Time Should be added. 2. App- On the Visit Plan, Visited, Memo the SN Number should be SR Number for RSO, Distributor, Supervisor, . 3. On Critical Retailers Pop-up Prepaid Sim must not be in Taka, must be in pcs. 4. App- On the Retailer Panel SIM Issue no error message is showing. 5. App- Top-Up Pin View (X) issue. 6. App- On every Edit Field Keyboard Next button must not work inappropriately. (Next Button click should be stopped). 7. App- Reatiler Panel Return View (Scroll) issue. 8. App- SIM Delivary Issue. 9. App- On Retailer Panel Dashboard SIM showing 0 but in stock report showing SIM Quantity 3 10. Critical Retailer, Products count must be only integer number. 11. App- Active RSO view Issue. 12. App- On the KPI Report Achievement data are showing but in Dashboard no data are showing for achievement. 13. Web- On the Current Offer Add Page DIstributor must have zone selection feature. 14. Web- Current offer Add issue for Distributor & Staff Role. 15. Web- Staf Role Issue. 16. App- Commission Structure is not showing for RSO. 17. App- EV Return is not working. 18. App- In RSO Salary Acknowledgement after submitting a complain it's showing multiple time for Distributor user. 19. App- No Remarks field for Complains for DIstributor user. 20. App- In Message Notification JPEG format need to include and uploaded image on web does not show in the app. 21. App- Notification for RSO not working. 22. Web- Poin Creation for Distributor is not working. | 1. For Critical Retailers, ZERO_SIM name Should be LOW_STOCK 2. App- for DD users on the Visited page the RSO visit count should be only visit count for each Retailer one time.
| FR 5 | 1. App & Web- Merchandiser Notifications need to check again. 2. App- In Merchandiser Stock & Issue not working, Price must be hidden. 3. App- Merchandiser POSM Product Return & Dismantale quantity validation issue. 4. Web- Merchandiser point creation issue.