## Sheet1
| SL. | FR Number | UAT Feedback | Business Observation | Status
UAT Day-3 | 18 | FR 30 | 1. App- On the login page "Login With User UserID/Phone" alignment should be the Center position of the phone. 2. App+Web- View As RSO for ZM needs to check in the RSO Activity Log. 3. App- Dashboard Menu, Notification, and some others should be added for Activity Count. |  | Pending
| 19 | FR 29 | 1. Web- Campaign Create is not showing in the Notice Board creation. 2. Web-UI Related Issue (Campaign Value is showing selected but actually not selected), in the Update feature. |  | Pending
| 20 | FR 28 | Passed | 1. App+Web- Dropdown and Implementation for (GA, Recharge, Revenue). (Business Observation) | Passed
| 21 | FR 27 | 1. Web+App- Today’s sales RSO apps and Total Report need data processing. 2. Web- Existing Sales By RSO. | 1. On the Reports "Ammount" need to change to "Count". | Passed
| 22 | FR 19 | Passed |  | Passed
| 23 | FR 18 | App- UI Pin Cancel properly not working in all device. |  | Passed
| 24 | FR 15 | Passed | 3 Lacks Retailer Data Upload Need to check in Live DB | Passed
| 25 | FR 16 | 1. App- Distributor Location, and Retailer Location need to add. 2. Need All Retailer Locations 3. Need All Distributor Locations Need Discussion with Mairaj Vaai | 1. App- Requirement Change needed 2. Need All Site Locations 3. Need All Retailer Locations 4. Need All Distributor Locations | Pending
| 26 | FR 26 | 1.App+Web- The Campaign needs to check with Mairaj Vaai. (Pending for Mairaj Vaai's Feedback) |  | Pending
| 27 | FR 7 | 1. App- Same Feedback as RSO View Feedback. (UAT Not Conducted) |  | Pending
| 28 | FR 9 | 1. App- All Transaction must be stopped for Zm as View as RSO and the message should be "You are not authorized to perform this" |  | Pending
| 29 | FR 14 | Passed |  | Passed
| 30 | FR 20 | 1. RSO App Side found ok Initially, dependency on Retailer App. (Need Data (Demand Request from Retailer App) |  | Pending