## Sheet2
Day | SL. | FR Number | Issue | Status
| 1 | FR 2 | Technical
| 2 | FR 3 | Data Dependency
| 3 | FR 4 | Technical
| 4 | FR 8 | API and Technical
| 5 | FR 9 | Technical
| 6 | FR 10 | Technical
| 7 | FR 11 | Technical
| 8 | FR 12 | Web- UI and Data Type change
| 9 | FR 13 | App- UI Change.
| 10 | FR 15 | No Issue from Our (PTSL Side)
| 11 | FR 20 | No Issue from Our (PTSL Side)
| 12 | FR 21 | App- Need Loader Image or GIF for Every Image Fileds
| 13 | FR 22 | Data Dependency
| 14 | FR 23 | 1. Technical. (Critical Issue) 2. Data Dependency.
| 15 | FR 25 | App- need Birtthday Templat
| 16 | FR 1 | 1. Web Development (User Matrix) 2. API 3. Valid Test Data | 1. Web- EV Return is not working. (Mamun Vaai + Abdullah Vaai)
| 17 | FR 5 | 1. Web Development (User Matrix) 2. API 3. Valid Test Data
| 18 | FR 7 | 1. Web Development (User Matrix) 2. Valid Test Data
| 19 | FR 16 | 1. API
| 20 | FR 26 | Pending from BL Side (Need Information from Mairaj Vaai)
| 21 | FR 28 | Web- API
| 22 | FR 29
| 23 | FR 30 | App- Dashboard Menu, Notification, and some others should be added for Activity Count. (Pending)
| 24 | FR 6 | Pending from BL Side
25
26
27
28
29
30
31

## Sheet1
Day | FR Number (Fixation UAT) Plan | Remarks | Clean Passed FR
Day-01 (25-10-2022) | FR 2, FR 3, FR 4, FR 8, FR 9, FR 10, FR 11, FR 12, FR 13, FR 15, FR 20, FR 21, FR 22, FR 23, FR 25 |  | FR 14, FR 17, FR 18, FR 19, FR 24, FR 27
Day-02 (26-10-2022) | FR 29, FR 30, FR 28, FR 6, FR 26, FR 1, FR 5, FR 7, FR 16