## Sheet1
SL | FR No | API/ Web/ App | Observation | Remarks | Status
1 | FR 20 | API + App | 1. Retailer demand status remain unchanged in retail app after delivering the product, In RSO app fulfilled demands carts needs to cleared out from the list.
2 | FR 1 | API | 1. API- For EV Return (BalancedReturnRSOList) need Status Code.
3 |  | API | 2. API- In the EV Return API (SaveStockReturn) the response must be in corrected format (Status Code, Message, Data in the Object).
4 |  | API/ Web/ App | 3. Users Matrix (RSO, Merchandiser, Supervisor, ZM) Development for "Notification", "Current Offer", and "Commission Structure".
5 | FR 16 | API | 1. Need Completed API to Provide Site location, Distributor location, retailer location in app
6 | FR 5 | API/ Web/ App | 1. Users Matrix (RSO, Merchandiser, Supervisor, ZM) Development for "Notification", "Current Offer", and "Commission Structure".
7 | FR 7 | API/ Web/ App | 1. Users Matrix (RSO, Merchandiser, Supervisor, ZM) Development for "Notification", "Current Offer", and "Commission Structure".
8 | FR 9 | API/ Web/ App | 1. Users Matrix (RSO, Merchandiser, Supervisor, ZM) Development for "Notification", "Current Offer", and "Commission Structure".
9 | FR 1 | API/ App | 1. Need Change for Stock Update of RSO RSO can not stock Itopup, need to remove itopup validation.
10 |  | API/ App | 2. For DD all RSO Itopup balance list must show.
11 |  | API/ App | 3. DD can see all RSO Itopup balance list then click on a specific RSO, enter DD pin, can edit the balance, and Return the balance after confirmation.
12 | FR 29 | Web | 1. Need change in the web, need multiple Campaign Notice upload and save feature in one UI page.
13 | FR 2 | Web | 1. Web+App- Year uploaded 2000 on web changes to 1990 year.