## Sheet1
Summery
| Passed | 18
| Passed With Observation | 5
| Failed | 7
| Total | 30
FR Number | Issue Description | Issue Type | FR Status
FR 14 | N/A | N/A | Passed
FR 17 | N/A | N/A | Passed
FR 18 | N/A | N/A | Passed
FR 19 | N/A | N/A | Passed
FR 24 | N/A | N/A | Passed
FR 27 | N/A | N/A | Passed
Date: 25-10-2022 | UAT Round 4 Feedback and Observation
FR Number | Issue Description | Issue Type | FR Status
FR 2 | 1. Web- Received Date column needed in Excel Export. | New Observation | Failed
FR 3 | OK |  | Passed
FR 4 | 1. Distance Parameter title needs to be added (KM/Mile/M) | Business Observation | Passed With Observation
FR 8 | 1. Other operator sales data needs to be optional | Business Team will check with DMS | Passed With Observation
FR 9 | 1. Not Run for too many data mismatches | New Observation with Test Data level issue | Failed
FR 10 | OK |  | Passed
FR 11 | OK |  | Passed
FR 12 | OK |  | Passed
FR 13 | 1. If provided pin is wrong, still showing success. (Need to skip pin input part) App- UI Change. | New Observation | Passed With Observation
FR 15 | 1. To be checked in live due to technical issue. | Will be checked after Live Deployment | Passed With Observation
FR 20 | 1. Retailer demand status remain unchanged in retail app after delivering the product, In RSO app fulfilled demands needs to cleared out | New Business Observation | Passed With Observation
FR 21 | OK |  | Passed
FR 22 | OK |  | Passed
FR 23 | 1. Web- RSO Footsteps View, Need Selected Point Cancel option. | Issue found | Failed
2. Web- RSO Check-in, Check-out point Data.
FR 25 | 1. Couldn't upload birth date (single data Item issue) | Issue found in Single Item but multiple items are found OK | Failed
Date: 26-10-2022 | UAT Round 5 Feedback and Observation | Issue Type | FR Status
FR 30 | 1. All Fixation Feedback are solved | N/A | Passed
| 2. App crashes when going to bar/unbar from ZM access (observation) | New Business Observation
FR 26 | 1. All Fixation Feedback are solved | N/A | Passed
| 2. Need To be discussed about (Campaign) (Pending for BL Business Side) | Old (Pending for Business Side)
| 3. Commission Structure, and Current offer feature working as expected. | N/A
FR 6 | No Feedback | N/A | Passed
FR 7 | 1. Valid Data level Issue | Old | Failed
| 2. Previous Feedback Included | Old
FR 1 | 1. Valid Data level Issue | Old | Failed
| 2. Previous Feedback Included | Old
FR 28 | 1. All Fixation Feedback are solved | N/A | Passed
| 2. ZM should have the site info view (Pending for confirmation from Tareq Vaai) | New Business Observation
FR 16 | 1. Initially Passed but Data need To be checked in live | N/A | Passed
FR 5 | 1. For stock add, product type & product, needs to be in accessing order (Solved) | N/A | Passed
| 2. If the number is not valid or not under the RSO app forces user to logout from RSO App. (Solved) | N/A | Passed
| 3. In Add stock total column to be removed | Fixation Feedback | Failed
| 4. Return option needs to be fixed, currently quantity can be updated but then it returns with something went wrong | Fixation Feedback | Failed
| 5. If the quantity is higher than the stock quantity app automatically loges out | Fixation Feedback | Failed
| 6. Issue date validation should be as same as RSO | Fixation Feedback | Failed
| 7. Dashboard Issue POSM data showing all wrong | Fixation Feedback | Failed
| 8. Error massage needs to be changed for out of scope retail for merchandizers | Fixation Feedback | Failed
| 9. Once POSM is issued, Issue screen should be minimized, same for dismantling/return | Fixation Feedback | Failed
| 10. Dismantling/return list is not updating | Fixation Feedback | Failed