## Sheet1
FR Number | Issue Description | Issue Type
FR 2 | 1. Web- Received Date column needed in Excel Export. | New
FR 3 | OK
FR 4 | 1. Distance Parameter title needs to be added (KM/Mile/M) | Business Observation
FR 8 | 1. Other operator sales data needs to be optional | Business Team will check with DMS
FR 9 | 1. Not Run for too many data mismatches | New Observation with Test Data level issue
FR 10 | OK
FR 11 | OK 1. PIN input box size not same for all digit (Solved)
FR 12 | OK 1. Report: In status column needs to add (Success/Failed) (solved) 2. New column to be added with Request type; Bar/Unbar (solved)
FR 13 | 1. If provided pin is wrong, still showing success. (Need to skip pin input part) App- UI Change. | New Observation
FR 15 | 1. To be checked in live due to technical issue. (Will be checked after Live Deployment)
FR 20 | 1. Retailer demand status remain unchanged in retail app after delivering the product. 2. In RSO app fulfilled demands needs to cleared out | 1. Fixation 2. (Business Observation)
FR 21 | OK
FR 22 | OK
FR 23 | 1. Web- RSO Footsteps View, Need Selected Point Cancel option. 2. Web- RSO Check-in, Check-out point Data. | 1. Fixation
FR 25 | 1. Couldn't upload birth date (single data Item issue) | Fixation